KAMLIFE COACH

Founder Setup Manual

Every single thing only you can do, in the order it has to happen.

Week of Monday 3 August 2026

Prepared for: Koketso Mokgokolo

Covers: company registration, bank, domain, WhatsApp Business number, Twilio, the four message templates, PayFast, POPIA, and the exact settings that make the bot go live.

How to read this Part 1 is your week — five days, what to do each day. Start there. Part 2 is the instruction manual — every task, every click, in full. Go to it when you sit down to actually do a task. Part 3 answers "will they approve it?" for each gate — what they check, what gets people rejected, and how we are set up to pass first time. Part 4 is a one-page tick list. Part 5 is what to send me when you're done. Nothing here needs code. If a step needs code, it says "send this to Claude" and I do it.

One honest note: websites move their buttons. Where a menu name here doesn't match exactly what's on your screen, the sequence is still right — look for the nearest equivalent wording. Prices and waiting times are accurate as of the first week of August 2026; treat them as close, not gospel.

# Part 0 — Read this before you touch anything

## 0.1  The one decision everything hangs on: which phone number

This is the single most expensive mistake available to you this week, so read it twice.

Your KamLife WhatsApp is +27 65 882 9664. Beauty, Beatrice, Mamamunchi, Jeepy, Puntsa, Bonolo, Kamogelo and Tshiamo are all in that chat list. You send them voice notes off your phone every day.

The moment a number is connected to the WhatsApp Business API, the WhatsApp app on the phone stops working for that number. Permanently, for as long as it stays connected. You cannot open the app and send a voice note from it any more. Every message on that number goes through the bot from then on.

So: buy a new SIM for the bot. Do not use 065 882 9664. Walk into any Vodacom / MTN / Telkom / Cell C shop, or a Shoprite / Pep / Spar till, and buy a prepaid starter pack. R5 to R50. RICA it in your name (bring your ID and proof of address). Put it in an old phone or a dual-SIM slot. It only has to do two things: receive one SMS (or one voice call) during setup, and stay alive. NEVER install WhatsApp or WhatsApp Business on it. If WhatsApp is registered on a number, Meta refuses to connect it to the API until that account is deleted. Keeping it clean saves you a whole extra step. Your 065 882 9664 stays exactly as it is — your human coaching line, with your voice notes, untouched.

Two follow-ups on that:

- Do NOT buy the number through Twilio. Twilio can sell +27 numbers but South Africa is an address-regulated country (ICASA), so it drags you into a documents-and-approval process you don't need. A prepaid SIM from a shop is faster, cheaper and works identically.

- Write the new number down the second you have it. It goes into four different places later: Meta, Twilio, Railway, and your website button.

## 0.2  The order, and why you can't shuffle it

Each of these hands a piece of paper or a number to the next one. Doing them out of order means sitting and waiting.

| This... | ...produces | ...which is required by |
| --- | --- | --- |
| CIPC company registration | Registration number CoR14.3 certificate | Bank account, PayFast, Meta verification, Information Regulator, privacy policy |
| Domain name | kamlifecoach.co.za | Business email, Meta verification (they check the website) |
| Business bank account | Account in the company's name | PayFast (they pay out to it) |
| Meta Business Verification | A verified business portfolio | The WhatsApp sender. Nothing WhatsApp happens before this. |
| WhatsApp sender approved | Your live +27 bot number | The four templates, then proactive messages |

The long pole is Meta Meta Business Verification takes 1 to 5 working days and needs your CIPC certificate. That is why CIPC is Monday morning and nothing else. You get three attempts at Meta verification. Three. Part 3 of this document exists so you use one.

## 0.3  What the week costs you

| Item | Cost | Notes |
| --- | --- | --- |
| CIPC name reservation | R50 | Four name options in one application |
| CIPC company registration | R125 | R175 total with the name reservation |
| Prepaid SIM for the bot | R5 – R50 | Once off |
| .co.za domain | R80 – R150 / year | Registrar-dependent |
| Business email | R0 – R130 / month | Zoho Mail has a free tier; Google Workspace is paid |
| Bank account | R0 – R120 / month | Several banks do free business accounts for startups |
| PayFast account | R0 to open | They take a cut per transaction — check their current rate |
| Meta Business Verification | Free |  |
| Information Officer registration | Free | Information Regulator |
| Twilio | Already funded | You pay per WhatsApp conversation |
| Railway hosting | Already running |  |

Realistic total to get off the ground this week: about R400 once-off, plus your existing monthly hosting.

# Part 1 — Your week, day by day

Five days. Each day has one thing that matters and a few small ones. If a day slips, the ones after it slip too — the Monday task is the one that cannot slip.

## MONDAY 3 August  —  Register the company. Nothing else matters today.

| Do | How long | Full instructions |
| --- | --- | --- |
| Register KamLife at CIPC on BizPortal | 45 min | Part 2, Task 1 |
| Buy the domain kamlifecoach.co.za | 20 min | Part 2, Task 2 |
| Buy and RICA the bot's prepaid SIM | 30 min | Part 2, Task 3 |

## TUESDAY 4 August  —  Bank, email, and start the Meta clock the second CIPC lands.

| Do | How long | Full instructions |
| --- | --- | --- |
| Open the business bank account | 1–2 hrs | Part 2, Task 4 |
| Create privacy@ and kam@ on your domain | 30 min | Part 2, Task 5 |
| Create the Meta Business Portfolio | 20 min | Part 2, Task 6 |
| Submit Meta Business Verification (needs the CIPC certificate) | 45 min | Part 2, Task 7 |

## WEDNESDAY 5 August  —  Money and law, while Meta reviews.

| Do | How long | Full instructions |
| --- | --- | --- |
| Open the PayFast merchant account | 45 min | Part 2, Task 10 |
| Register yourself as Information Officer | 30 min | Part 2, Task 11 |
| Accept the OpenAI and Twilio data agreements | 15 min | Part 2, Task 12 |
| Send me your registration number + Information Officer name | 2 min | Part 2, Task 12 |

## THURSDAY 6 August  —  WhatsApp. Only possible if Meta verification came back.

| Do | How long | Full instructions |
| --- | --- | --- |
| Register the WhatsApp sender in Twilio | 45 min | Part 2, Task 8 |
| Submit the four message templates | 45 min | Part 2, Task 9 |
| Point the Twilio webhook at the app | 10 min | Part 2, Task 8, step 9 |

## FRIDAY 7 August  —  Wire it up and prove the money works.

| Do | How long | Full instructions |
| --- | --- | --- |
| Set every Railway variable | 20 min | Part 2, Task 13 + Appendix B |
| Run a R1 PayFast payment end to end | 30 min | Part 2, Task 14 |
| Switch the proactive messages on | 5 min | Part 2, Task 15 |
| Text 20 people | the rest of the day | The actual business |

If Meta verification has not come back by Thursday That is normal and it is not a problem you can solve by refreshing. Do Friday's Railway work anyway, and text the 20 people. The sandbox number still works for testing. The one thing you must not do is submit verification a second time while the first one is still pending. That burns one of your three attempts.

# Part 2 — The instructions

Every task, in full. Each one tells you where to go, what to have ready, what to type, and how to know it worked.

## Task 1 — Register the company (CIPC, via BizPortal)

Where: bizportal.gov.za     Cost: R175     Time: 45 minutes     Result: 1–5 working days

### Have ready before you start

- Your South African ID number and a clear photo/scan of your ID

- Your cellphone (they SMS you a one-time code)

- Your email address

- Your residential address

- A debit or credit card

- Four company name options, written down — see the naming note below

### The steps

- Go to bizportal.gov.za. If you have never used CIPC before, you need a CIPC customer code first: click Register as a Customer and complete it. You'll get a customer code and password by SMS and email. This is not the company — it's your login.

- Log in with your ID number and that password. Choose Register a Company.

- Choose company type: Private Company (Pty) Ltd. Not a Non-Profit, not a Personal Liability company. One director is enough — you.

- Enter your four name options. CIPC works down the list and gives you the first one that's free. See the naming note — this choice affects your WhatsApp approval later.

- Enter director details: your ID number, full names, address, contact details. You will be asked to verify your identity — usually a one-time SMS code, sometimes a facial/biometric check through the portal.

- Financial year end: pick February unless you have a reason not to. It lines up with SARS and every SA accountant expects it.

- Pay R175 by card. Submit.

- BizPortal then offers you a set of extras on the same screen. Take these three, they are free and you will need them:

  - SARS income tax number — issued automatically with the registration

  - B-BBEE EME affidavit — free, and any corporate client will ask for it

  - Domain name and bank account offers — you can skip these here, you're doing them yourself in Tasks 2 and 4

- Wait. Name approval and registration come back by email, typically 1–5 working days, often faster.

### What you get, and what you must save

Download every PDF they send and put them in one folder on your phone and your laptop. You will upload them to Meta, PayFast and the bank this week.

- CoR14.3 — Registration Certificate. THIS is the one Meta and PayFast want.

- CoR14.1 — Notice of Incorporation

- CoR15.1A — Memorandum of Incorporation (MOI)

- Your registration number, in the format 2026 / 123456 / 07

Naming: this decision reaches all the way to WhatsApp Later, Meta has to approve "KamLife Coach" as your WhatsApp display name. Meta approves a display name much more easily when it clearly relates to your registered legal business name. If your company is registered as something unrelated, you are arguing with a reviewer for no reason. So make all four options contain the word KamLife. For example, in order of preference: 1. KamLife Coach (Pty) Ltd 2. KamLife Coaching (Pty) Ltd 3. KamLife Health (Pty) Ltd 4. KamLife Wellness (Pty) Ltd Avoid words CIPC treats as restricted: anything suggesting you are a bank, insurer, university, or government body. Avoid "medical", "clinic", "doctor", "therapy" and "treatment" — those cause you problems at CIPC, at Meta, and with the Health Professions Council. You are a coach, not a clinician, and the name should say so.

## Task 2 — Get the domain name

Where: any SA registrar — domains.co.za, afrihost.com, xneelo.co.za     Cost: R80–R150/yr     Time: 20 min

You need this for two reasons: the business email address your privacy policy already promises, and because Meta looks at your website when it verifies you.

- Search for kamlifecoach.co.za. If it's gone, try kamlife.co.za or kamlifecoach.africa. Stay away from .com if you can — .co.za reads as local and local is your whole market.

- Buy it. Register it in the company's name and use your own email as the contact.

- Do not configure anything else yet. Once you have it, send me the domain name and I'll give you the exact DNS records to paste in so it points at the live app.

Why Meta cares about this During Business Verification, Meta looks for a live website on HTTPS that matches the business you say you are. Right now the app answers on a railway.app address, which works but looks like a test project. kamlifecoach.co.za, live, with your privacy policy on it, is one of the strongest signals a small business can give a Meta reviewer. Get the domain Monday so it's live before you submit on Tuesday.

## Task 3 — Get the bot's phone number

Where: any mobile shop, supermarket till or Pep     Cost: R5–R50     Time: 30 min

Read Part 0.1 again if you skipped it. This is the number your clients will message forever. It is not 065 882 9664.

- Buy a prepaid starter pack. Any network. Vodacom and MTN have the best rural coverage, which matters for your market.

- RICA it in your name or the company's name — bring your ID and a proof of address. An un-RICA'd SIM gets cut off and takes the bot with it.

- Put it in a phone and confirm it can receive an SMS and an ordinary voice call. That's the whole test.

- Do NOT install WhatsApp on it. Do not "just check" whether WhatsApp works on it. If WhatsApp registers on this number, you have to delete that WhatsApp account and wait before Meta will let the API have it.

- Put R50 airtime on it and set a calendar reminder to keep it active. A dead SIM is a dead business.

Write it here: ______________________________

## Task 4 — Open the business bank account

Where: Capitec Business, FNB, Standard Bank, Nedbank, TymeBank     Time: 1–2 hrs

PayFast pays your clients' money into this account. It must be in the company's name, not your personal account, once you are a (Pty) Ltd.

### Take with you

- CoR14.3 registration certificate

- Your ID

- Proof of address, under 3 months old (municipal bill, bank statement, lease)

- Your company registration number

### The steps

- Compare monthly fees first — several banks waive them for the first 12 months for a newly registered company. Ask for that explicitly; they don't always offer it.

- Open the account. Some banks now do the whole thing in-app once CIPC data is verified, so check the app before you drive anywhere.

- Ask for a stamped bank confirmation letter before you leave. PayFast asks for exactly this and you do not want a second trip.

- Turn on notifications for every deposit. When R199 lands, you want to feel it.

## Task 5 — Create the business email addresses

Where: zoho.com/mail (free tier) or workspace.google.com     Time: 30 min

Your privacy policy promises a privacy address. If a client emails it and nothing happens, that is a POPIA problem, not a cosmetic one.

- Create two addresses on your new domain:

  - privacy@kamlifecoach.co.za — legally required to work

  - kam@kamlifecoach.co.za — what you give Meta, PayFast and the bank

- The registrar will show you MX records to add. Add them. If you get stuck, send me a screenshot.

- Send a test email to each one from your Gmail and confirm it arrives.

Use kam@kamlifecoach.co.za for Meta and PayFast A business email on your own domain is a verification signal. A gmail.com address is a small red flag on every application form you are about to fill in this week. It costs you thirty minutes to remove that flag.

## Task 6 — Create the Meta Business Portfolio

Where: business.facebook.com     Cost: free     Time: 20 min

This is the container Meta puts your WhatsApp Business Account inside. Get the details exactly right here, because Task 7 checks them against your CIPC documents character by character.

- Go to business.facebook.com and log in with your personal Facebook account. You need one — Meta has no business-only login. Use an account with your real name on it.

- Turn on two-factor authentication on that Facebook account before you go further. If it gets hacked, your WhatsApp number goes with it.

- Click Create a business portfolio (older wording: "Create account").

- Business name: type your registered name exactly as it appears on the CoR14.3 — including "(Pty) Ltd". Not "KamLife", not "Kamlife coach". Copy and paste it from the certificate.

- Your name: your full legal name as on your ID.

- Business email: kam@kamlifecoach.co.za. Confirm it from your inbox.

- In Business Settings → Business Info, fill in every field: address (your real physical address, never a PO Box), phone, and website https://kamlifecoach.co.za. Empty fields are a reason to reject.

## Task 7 — Meta Business Verification  ★ the gate

Where: business.facebook.com → Business Settings → Security Centre     Cost: free     Result: 1–5 working days

You get three attempts. Total. Meta allows a business portfolio to apply for verification three times. After that you are into appeals and support tickets, which for a small South African business can take weeks. So do not submit until every item on the checklist below is true. Twenty minutes of checking now is worth a fortnight.

### Before you submit — every one of these must be true

☐   The business name in your Meta portfolio matches the CoR14.3 character for character, including "(Pty) Ltd"

☐   The address in Meta matches the address on your supporting document — same street, same spelling, same postal code

☐   It is a physical address. Not a PO Box. Meta rejects PO Boxes outright.

☐   The phone number you give is one you can actually answer — they may call or SMS it

☐   kamlifecoach.co.za loads, on https, and is not a parked "coming soon" page

☐   The website mentions the business name and has a way to contact you

☐   Your supporting document is dated within the last 12 months

☐   Your business email is on your own domain, not gmail.com

### The steps

- Business Settings → Security Centre → under Business Verification, click Start verification.

- Country: South Africa.

- Legal business name: paste from the CoR14.3.

- Business registration number: your CIPC number, 2026/123456/07 format. Type the slashes.

- Address, phone, website: as above, all matching.

- Upload your documents. Upload two, not one — it gives the reviewer a second chance to match you:

  - CoR14.3 Registration Certificate (this is the primary one)

  - A business bank statement showing the company name and address, OR a utility bill, OR your B-BBEE affidavit — under 12 months old

- Choose a confirmation method: SMS, phone call, or email to your domain. Email to kam@kamlifecoach.co.za is the easiest to control.

- Submit. Then leave it alone. Do not resubmit, do not edit the business details while it is pending — editing mid-review can fail the review.

- You get an email when it's decided, and the status shows in Security Centre. If it is rejected, read Appendix C before you touch attempt number two.

## Task 8 — Register the WhatsApp sender in Twilio

Where: console.twilio.com → Messaging → Senders → WhatsApp senders     Time: 45 min

Do this only after Meta verification comes back approved. You can start it before, but the sender sits in limbo and it just confuses things.

### Have ready

- The new SIM, in a phone, in your hand — a code arrives during the process

- Your Facebook login for the verified business portfolio

- Your domain, business email, and a one-line business description

### The steps

- Twilio Console → Messaging → Senders → WhatsApp senders → Create new sender.

- Twilio opens Meta's embedded signup in a pop-up. Allow pop-ups. Log in to Facebook when asked.

- Select your existing verified business portfolio. Do not let it create a new one — a new one is unverified and you're back to square one.

- Create the WhatsApp Business Account. Name it KamLife Coach.

- Add the phone number — your new SIM, in international format: +27XXXXXXXXX. Drop the leading 0.

- Choose SMS or Voice call for verification. The code arrives in seconds. Type it in.

- Fill in the WhatsApp business profile. This is what clients see when they tap your name — treat it as a shopfront:

| Field | What to put |
| --- | --- |
| Display name | KamLife Coach |
| Category | Health & Wellness (if that exact one isn't offered, pick Fitness, then Professional Services) |
| Description | WhatsApp coaching for South Africans. Log your food, steps and training by text, photo or voice note. R199 a month. |
| Website | https://kamlifecoach.co.za |
| Email | kam@kamlifecoach.co.za |
| Address | Your real business address |
| Profile photo | The KamLife logo. Square, clear, no text-heavy image. |

- Submit. Meta reviews the display name separately from everything else — usually minutes to 48 hours.

- When the sender shows as approved, set the webhooks in Twilio. Still under the sender's settings, find Endpoint configuration (older wording: "When a message comes in") and set:

| Setting | Value | Method |
| --- | --- | --- |
| When a message comes in | https://kamlifecoach.co.za/twilio/whatsapp | HTTP POST |
| Status callback URL | https://kamlifecoach.co.za/webhook/status | HTTP POST |

Until the domain points at the app, use the Railway address instead https://kamlife-coach-production.up.railway.app/twilio/whatsapp https://kamlife-coach-production.up.railway.app/webhook/status Both work. Send me the domain and I'll switch it over properly, then you change these two fields once.

- Test it: from your own phone, WhatsApp the new number and say "hi". Coach K must answer. If nothing comes back, screenshot the Twilio Monitor → Logs → Errors page and send it to me.

What you get on day one A brand-new number starts on the lowest messaging tier: 1,000 business-initiated conversations per rolling 24 hours. With 20 clients that is not a ceiling you will feel. It rises automatically as your quality rating stays good. Clients replying to you is unlimited and always has been. The tier only counts conversations you start.

## Task 9 — Submit the four message templates

Where: console.twilio.com → Messaging → Content Template Builder     Time: 45 min     Result: usually same day

Here is the rule that makes these necessary. WhatsApp only lets you send whatever you like within 24 hours of the client's last message to you. Outside that window, every message is blocked unless it is a template Meta approved in advance.

Which means: without these four, a client who didn't message yesterday gets no morning message, no weekly check, and no failed-payment warning. The coach just goes quiet and you lose them without knowing why.

Run this first, and work from what it prints Ask me to run: npx tsx script/template-pack.ts It prints all four templates exactly as they must be typed, checks them against the mechanical reasons Meta rejects templates, and refuses to print a pack that would fail. The full text is also in Appendix A of this document so you can work straight from paper.

### For each of the four templates

- Content Template Builder → Create new.

- Content type: Text. Not Card, not Quick Reply, not List Picker.

- Template name: type it exactly as printed — lowercase, underscores, nothing else. kamlife_daily_plan, not "Kamlife Daily Plan".

- Language: English (en). Not en_ZA — that is not a Meta locale and it will fail.

- Body: copy the text from Appendix A exactly, including the blank lines. Do not tidy it up, do not add a greeting, do not add an emoji.

- Sample values: Meta demands one example per {{1}}. They are listed in Appendix A. Missing samples is the single most common rejection.

- Category: as listed in Appendix A. Three are UTILITY, one is MARKETING. Do not put all four in as UTILITY to save money — Meta re-categorises it, and that costs you a review cycle.

- Submit for WhatsApp approval. Repeat for all four. Submit all four the same day so they review together.

- When each is approved, copy its HX… SID and paste it into the matching Railway variable — the pairs are in Appendix A and Appendix B.

## Task 10 — PayFast merchant account

Where: registration.payfast.io     Cost: free to open     Result: 1–7 days

### Have ready

- CoR14.3 certificate and your registration number

- Your ID

- The stamped bank confirmation letter from Task 4

- Proof of address

- Your website URL

### The steps

- Register at registration.payfast.io. Account type: Business / Registered Company — not Sole Trader, now that you are a (Pty) Ltd.

- Enter the company details. The name must match CIPC. The bank account must be in the company's name — a personal account on a company application is the most common reason PayFast holds people up.

- Upload your FICA documents. All of them at once. A partial upload restarts the clock.

- Once verified, go to Settings → Integration and write down three values:

  - Merchant ID

  - Merchant Key

  - Passphrase — you set this yourself. Make it long and random. Save it somewhere you won't lose it.

- Send me those three and I put them in Railway — or put them in yourself using Appendix B. Never send the Merchant Key or Passphrase over WhatsApp or email.

- In PayFast, set the ITN / notify URL if it asks for one:

https://kamlifecoach.co.za/webhook/payfast

Your price is R199 a month with a 7-day free trial That is already set in the code and on the site. You decided it, from your own evidence: R250 is what you charge for manual coaching, and R500 had people complaining about money. If you change your mind about the price, tell me — it lives in one file and changes everywhere at once. Do not change it in PayFast only; the two will disagree and clients will be charged the wrong amount.

## Task 11 — Register as Information Officer (POPIA)

Where: inforegulator.bizportal.gov.za     Cost: free     Time: 30 min

You are storing South Africans' weight, meals, photos of their bodies and their health conditions. That is special personal information under POPIA. Every organisation that does this must register an Information Officer with the Information Regulator, and by law the officer's duties only start once that registration is done.

It is free, it takes half an hour, and skipping it is the kind of thing that ends a business rather than fining it.

- Go to inforegulator.bizportal.gov.za — the eServices portal. (The old registration portal was retired; if a search sends you somewhere else, come back to this address.)

- Create an account with your ID number and email.

- Choose Information Officer registration.

- Body type: Private Body. Enter the company name and CIPC registration number.

- Information Officer: yourself. For a company, the law makes the head of the organisation the Information Officer by default — that is you. Enter your ID, contact details and privacy@kamlifecoach.co.za as the contact address.

- Deputy Information Officer: optional while you are one person. Leave it, or add someone you trust.

- Submit. A registration certificate comes by email. Save that PDF — it is your proof of compliance and a corporate client will ask for it one day.

## Task 12 — Sign the two data agreements, and send me two values

Cost: free     Time: 15 min

POPIA says that when you let another company process your clients' data, there must be an agreement in place. Two companies process it for you: OpenAI (the coach's understanding) and Twilio (the messages themselves). Both publish a click-through agreement.

- OpenAI: log in at platform.openai.com, then open their Data Processing Addendum page and complete the form. Search their docs for "data processing addendum" if the menu has moved. Save the confirmation.

- Twilio: go to twilio.com/legal/data-protection-addendum and accept it against your account. Save the confirmation.

### Then send me these two values

Your privacy policy has two blanks in it that only you can fill:

| Blank | What it is | Where you get it |
| --- | --- | --- |
| [Information Officer Name] | Your full legal name | Your ID |
| [Company Registration Number] | The CIPC number | The CoR14.3, format 2026/123456/07 |

Send me those two and I fill them in and push. One minute of work — but until it is done, your published privacy policy has square brackets in it, and a Meta reviewer reading it sees an unfinished business.

## Task 13 — Set the Railway variables

Where: railway.app → project zoological-strength → KamLife-Coach → Variables     Time: 20 min

These are the switches that connect everything you did this week to the running app. Appendix B is the full list with exact spellings. Two things to know before you start:

- Variable names are case-sensitive and must be typed exactly. TWILIO_WHATSAPP_NUMBER, not Twilio_Whatsapp_Number.

- Every save triggers a redeploy that takes one or two minutes. Set them all, then save, rather than one at a time.

How to know it worked: WhatsApp the bot the single word

version

It replies with the running commit and a checklist of what is wired. Screenshot that reply and send it to me — it tells me in one picture what is live and what is missing.

## Task 14 — Prove the money works, before anyone pays you

Time: 30 min

- Ask me to put PayFast in sandbox mode. Run a test payment through the whole flow.

- Then switch to live and pay R1 with your own card, as if you were a client.

- Check all four of these actually happened:

  - The money left your account

  - It shows in the PayFast dashboard

  - The subscription flipped to active in the admin dashboard

  - The welcome message arrived on WhatsApp

- If any one of those four did not happen, stop and send me a screenshot. Do not sell anything until all four work. A client whose payment goes through and then hears nothing is a refund and a bad word to twenty people.

## Task 15 — Switch the proactive messages on

Time: 1 minute. Do it last.

There is a global killswitch holding back every message the coach sends first — the morning check-in, the evening accountability, the weekly review, the win-back. It is on deliberately, so the bot cannot message anyone before your own number is approved.

- Only once the WhatsApp sender is approved, the four templates are approved, and their SIDs are in Railway:

- Railway → Variables → delete PROACTIVE_PAUSED entirely (or set it to false).

- Watch the first morning batch go out. If anything reads wrong, screenshot it — and set PROACTIVE_PAUSED=true again. It is a switch, not a door; you can close it any time.

One thing already works while paused Critical payment alerts still go out even with proactive messaging paused. That is deliberate — a client whose payment failed must always hear about it, whatever else is switched off.

# Part 3 — "Are we sure they're going to approve this?"

Fair question, and the honest answer is: nobody can promise you a yes from Meta. What we can do is make sure that every reason they say no does not apply to you. Here is each gate, what they are actually checking, what gets small businesses rejected, and where you stand.

## 1.  CIPC company registration

Likelihood: Near certain, if the name is free

| What they check | What gets people rejected | Where you stand |
| --- | --- | --- |
| Is the name available and not restricted? | Name too close to an existing company; name implies banking, insurance, or medical practice | You submit four options with KamLife in each and avoid every medical word |
| Are the director's details verifiable? | ID verification fails | Your own SA ID, straightforward |

## 2.  Meta Business Verification

Likelihood: Strong — this is the one worth preparing for

| What they check | What gets people rejected | Where you stand |
| --- | --- | --- |
| Does a real registered business exist with this name? | The name in Meta doesn't match the certificate exactly | You copy-paste from the CoR14.3. No typing it from memory. |
| Does the document prove the name and address? | PO Box address; document older than 12 months; a document that doesn't show the address at all | Fresh CoR14.3 plus a bank statement, both under a month old, physical address |
| Is there a real website? | No website, dead link, http not https, a parked page | kamlifecoach.co.za live from Monday, on https, with a privacy policy on it |
| Does this look like a real business or a throwaway? | Gmail address, empty business info fields, brand-new Facebook account with no history | Domain email, every field filled, your real Facebook account |

## 3.  WhatsApp display name "KamLife Coach"

Likelihood: Strong

| What they check | What gets people rejected | Where you stand |
| --- | --- | --- |
| Does the display name relate to the verified business name? | Display name has nothing to do with the registered company | Registering as KamLife Coach (Pty) Ltd makes this a formality |
| Is it a real name, not a description? | Generic names — "Fitness Coach", "Best Deals", "Support" | "KamLife Coach" is a brand, not a category |
| Format | ALL CAPS, emojis, a URL, or a phone number in the name | Plain words, normal capitals |

## 4.  The four message templates

Likelihood: Strong — they are built to pass

| What they check | What gets people rejected | Where you stand |
| --- | --- | --- |
| Mechanical correctness | Placeholder at the start or end of the message; gaps in {{1}} {{2}} numbering; two variables side by side; missing sample values | The code checks all of these offline before you submit, and refuses to print a pack that would fail |
| Honest category | Declaring a promotional message as UTILITY to get the cheaper rate | Three are genuinely UTILITY. The win-back one is declared MARKETING because that is what it is. |
| Content | Promotional words in a utility template; health claims; guarantees; anything spammy | No "free", no "guaranteed", no weight-loss promise, no urgency language anywhere in the four |

## 5.  PayFast

Likelihood: Strong, but they are strict about one thing

| What they check | What gets people rejected | Where you stand |
| --- | --- | --- |
| FICA on the business and the person | Bank account not in the business's name; incomplete document upload | Company account from Task 4, all documents uploaded in one go |
| Is the business real and lawful? | No website; unclear what is being sold | Live site, one clear product at one clear price |

## 6.  The risk nobody mentions: health claims

This is the one place where a fitness product genuinely can fall foul of Meta's policies, so it is worth being precise about where you sit.

| Meta's line | Which side you are on |
| --- | --- |
| Selling medicines, supplements or medical devices through WhatsApp is restricted or prohibited | You sell coaching. You sell no product at all. Not affected. |
| Making medical claims — curing, treating or diagnosing a condition | The coach is built to refuse medical scope. Ask it about blood pressure medication or a diagnosis and it refers you to a doctor. That behaviour is not behind a feature flag — it cannot be switched off by mistake. |
| Weight-loss content that shames or promises results | None of the four templates mentions weight, a target, or a result. The coaching voice asks before it judges — that came from your own transcripts. |

Where you are genuinely exposed, and it is not Meta The real regulatory risk in this business is not WhatsApp approval. It is POPIA. You are storing photographs of people's bodies, their weight, and what they tell you about their health, on behalf of paying South African clients. That is why Task 11 is not optional and why the privacy address has to actually receive mail. Get those two right and you are in a stronger position than most small coaching businesses in the country.

# Part 4 — Master checklist

One page. Tick as you go.

### Company and money

☐   CIPC registered — registration number received

☐   CoR14.3, CoR14.1 and MOI saved in one folder

☐   SARS income tax number received

☐   B-BBEE EME affidavit downloaded

☐   Business bank account open

☐   Stamped bank confirmation letter in hand

☐   PayFast account approved

☐   PayFast Merchant ID, Key and Passphrase in Railway

☐   R1 live payment tested end to end, all four checks passed

### Identity online

☐   Domain bought

☐   Domain pointed at the app (send me the domain — I do the DNS)

☐   privacy@ and kam@ addresses working, both tested

☐   Privacy policy blanks filled (send me the two values)

### WhatsApp

☐   New prepaid SIM bought and RICA'd — WhatsApp NEVER installed on it

☐   Meta Business Portfolio created, details matching CIPC exactly

☐   Meta Business Verification submitted

☐   Meta Business Verification APPROVED

☐   Twilio WhatsApp sender registered

☐   Display name "KamLife Coach" approved

☐   Business profile filled in — photo, description, website, address

☐   Webhook set to /twilio/whatsapp

☐   Status callback set to /webhook/status

☐   You messaged the new number yourself and Coach K answered

### Templates

☐   kamlife_daily_plan submitted → approved → SID in Railway

☐   kamlife_weekly_check submitted → approved → SID in Railway

☐   kamlife_payment_failed submitted → approved → SID in Railway

☐   kamlife_checking_in submitted → approved → SID in Railway

### Law

☐   Registered as Information Officer — certificate saved

☐   OpenAI data processing agreement accepted

☐   Twilio data protection addendum accepted

### Go live

☐   TWILIO_WHATSAPP_NUMBER updated to the new number

☐   TWILIO_SMS_NUMBER set (payment alerts fall back to SMS)

☐   APP_URL set to the real domain

☐   "version" replied clean — screenshot sent to me

☐   PROACTIVE_PAUSED deleted

☐   Twenty people texted

# Part 5 — What to send me, and when

Six things. Each one unblocks something on my side that I cannot do without you.

| Send me | As soon as | What I do with it |
| --- | --- | --- |
| Your CIPC registration number and your full legal name | CIPC comes back | Fill the two blanks in the privacy policy and push it live |
| The domain name you bought | Monday | Give you the exact DNS records, then switch APP_URL over |
| The new bot phone number | You buy the SIM | Check every place the number is used and tell you what to update |
| PayFast Merchant ID, Key, Passphrase | PayFast approves | Wire the live payment path — send these securely, not over WhatsApp |
| The four HX… template SIDs | Meta approves each one | Confirm the wiring and check the proactive jobs actually fire |
| A screenshot of the "version" reply | Anything is set in Railway | One picture tells me what is live and what is still missing |

And the one thing that isn't on any list Text twenty people this week. Not next week, not after the number is approved — the sandbox works today. Right now the product has two real users in it. Every question about pricing, retention and how people actually behave is unanswerable at two. At twenty it starts answering itself, and everything in this document exists to serve that.

# Appendix A — The four templates, word for word

Type these exactly. Blank lines matter. Do not add a greeting, an emoji, or a full stop that isn't there.

## 1.  kamlife_daily_plan

| Field | Value |
| --- | --- |
| Template name | kamlife_daily_plan |
| Category | UTILITY |
| Language | English (en) |
| Content type | Text |
| Railway variable for the approved SID | TWILIO_DAILY_TEMPLATE_SID |

Without this: Nobody who was quiet yesterday hears from the coach today.

Body — copy everything between the rules:

Morning {{1}} — your KamLife plan for today is ready.

Today's one thing: {{2}}

Reply here to log your food, steps or session. Everything you have logged is still saved.

Sample values Meta requires (one per placeholder — do not leave these blank):

- {{1}} = Thandi   (the client's first name)

- {{2}} = Log one meal — even just what you had for lunch   (today's one action)

## 2.  kamlife_weekly_check

| Field | Value |
| --- | --- |
| Template name | kamlife_weekly_check |
| Category | UTILITY |
| Language | English (en) |
| Content type | Text |
| Railway variable for the approved SID | TWILIO_WEEKLY_TEMPLATE_SID |

Without this: The weekly review only reaches clients who happened to message that day.

Body — copy everything between the rules:

Your 7-day KamLife check is ready, {{1}}.

Sessions this week: {{2}}

Days you logged food: {{3}}

Reply *progress* for the full breakdown and what to fix first.

Sample values Meta requires (one per placeholder — do not leave these blank):

- {{1}} = Thandi   (the client's first name)

- {{2}} = 2 of 3   (sessions done vs planned)

- {{3}} = 5 of 7   (days food was logged)

## 3.  kamlife_payment_failed

| Field | Value |
| --- | --- |
| Template name | kamlife_payment_failed |
| Category | UTILITY |
| Language | English (en) |
| Content type | Text |
| Railway variable for the approved SID | TWILIO_PAYMENT_TEMPLATE_SID |

Without this: A client's subscription lapses and the first they know is the coach going quiet.

Body — copy everything between the rules:

Hi {{1}} — your KamLife payment of R{{2}} did not go through, so your coaching is on hold.

Reply *pay* and I will send you a fresh link. Nothing you have logged is lost.

Sample values Meta requires (one per placeholder — do not leave these blank):

- {{1}} = Thandi   (the client's first name)

- {{2}} = 199   (amount in rand)

## 4.  kamlife_checking_in

| Field | Value |
| --- | --- |
| Template name | kamlife_checking_in |
| Category | MARKETING — clients can mute MARKETING messages; this one is worth it anyway |
| Language | English (en) |
| Content type | Text |
| Railway variable for the approved SID | TWILIO_REENGAGE_TEMPLATE_SID |

Without this: There is no way back into a chat that has been silent for more than 24 hours.

Body — copy everything between the rules:

It is Coach K checking in. You have been quiet for a bit and I am not writing you off.

There is no catching up to do and nothing you logged is lost. Reply with one word and we start from today.

No placeholders, so no samples. That is deliberate: this one is sent from a code path that knows only a phone number, so a variable would arrive blank. Do not add one.

# Appendix B — Every Railway variable

railway.app → project zoological-strength → KamLife-Coach → Variables. Names are case-sensitive and must be typed exactly.

## Set these this week

| Variable | Value | When |
| --- | --- | --- |
| TWILIO_WHATSAPP_NUMBER | whatsapp:+27XXXXXXXXX | Sender approved |
| TWILIO_SMS_NUMBER | An SMS-capable Twilio number | Anytime — payment alerts fall back to SMS without it |
| APP_URL | https://kamlifecoach.co.za | Domain pointed at the app |
| PAYFAST_MERCHANT_ID | From PayFast → Settings → Integration | PayFast approved |
| PAYFAST_MERCHANT_KEY | From PayFast → Settings → Integration | PayFast approved |
| PAYFAST_PASSPHRASE | The one you set in PayFast | PayFast approved |
| TWILIO_DAILY_TEMPLATE_SID | HX… | kamlife_daily_plan approved |
| TWILIO_WEEKLY_TEMPLATE_SID | HX… | kamlife_weekly_check approved |
| TWILIO_PAYMENT_TEMPLATE_SID | HX… | kamlife_payment_failed approved |
| TWILIO_REENGAGE_TEMPLATE_SID | HX… | kamlife_checking_in approved |
| PROACTIVE_PAUSED | DELETE this variable | Absolutely last — everything else done |

## Already set — leave them alone

| Variable | What it does |
| --- | --- |
| TWILIO_ACCOUNT_SID / TWILIO_AUTH_TOKEN | Your Twilio login. Unchanged by any of this week's work. |
| DATABASE_URL | The database. Never touch. |
| OPENAI_API_KEY | The coach's understanding. |
| SENTRY_DSN | Error alerting — live. |

## Optional, when you get to it

| Variable | What it unlocks |
| --- | --- |
| MEDIA_BASE_URL | Exercise GIFs and the portion-guide images. Static images work today without it. |
| ELEVENLABS_API_KEY | Voice replies. Rotate the current key — it was exposed in the codebase once. |
| VITE_HERO_VIDEO_URL | A video on the landing page. Build variable, not runtime. |

# Appendix C — If something gets rejected

Rejection is normal and almost always mechanical. Do not resubmit the same thing hoping for a different reviewer — with Meta you only get three tries.

## Meta Business Verification rejected

- Read the actual reason in Security Centre. It is specific, even when it reads like boilerplate.

- Nine times out of ten it is one of four things:

  - A name mismatch — even "Pty Ltd" vs "(Pty) Ltd"

  - An address mismatch between what you typed and what the document shows

  - The website is down, isn't https, or is a parked page

  - The document is over 12 months old, or a photo too blurry to read

- Fix the exact thing named. Change nothing else. Then use attempt two.

- If you are down to your last attempt, send me the rejection text before you resubmit and we go through it line by line.

## Display name rejected

The number still works — it just gets capped at 250 business-initiated messages per day until the name is fixed, and Meta may disconnect it if it is left. So fix it, don't ignore it.

- Change the display name so it plainly matches your registered business name, then resubmit from the WhatsApp Manager.

- Do not try clever variations. "KamLife Coach" against a company called KamLife Coach (Pty) Ltd is the version that passes.

## A template rejected

- Meta tells you the category of failure but rarely the exact line. Ask me to re-run the pack script — it checks the mechanical rules again.

- Fix and resubmit. Templates have no attempt limit — this one you can iterate on freely.

- If Meta re-categorises a UTILITY template to MARKETING, accept it. Arguing costs days and the message still sends.

## PayFast held up

- Almost always a FICA document. Call them — PayFast support answers, and one phone call beats a week of email.

- The most common cause is a bank account that isn't in the registered company's name.

## The bot doesn't reply on the new number

- Check the webhook URL in Twilio has no typo and no trailing slash.

- Check TWILIO_WHATSAPP_NUMBER in Railway includes the whatsapp: prefix and the +27 country code.

- Twilio Console → Monitor → Logs → Errors. Screenshot whatever is there and send it to me. That page names the problem almost every time.

Nothing in this document requires you to write a line of code, and nothing in it is optional except the items marked optional. Work down it in order. When you get stuck, send me a screenshot of the screen you are stuck on rather than a description of it — the screen tells me things a description can't.